## AllFeaturesTestExecutionInfo
Sprint Details | Test Case ID | Test ID | Scripting | Defect ID/Reason | Test Data | Status of Execution | Feature File Name | New Execution | Report file Name
Sprint 1 | 843959 | AT_AFF_036 | Completed |  | Done | Done | ApplicationFinancialFacility_608
Sprint 1 | 862019 | AT_AFF_040 | Completed |  | Done | Need to validate | ApplicationFinancialFacility_608
Sprint 1 | 285050 |  | Not started | IIS KT Need |  | Descoped
Sprint 1 | 296063 | AT_AFF_048 | Completed |  | Done | Done | ApplicationFinancialFacility_608
Sprint 2 | 294466 | AT_AFF_052 | Completed |  | Done | Done | ApplicationFinancialFacility_608
Sprint 2 | 299883 | AT_AFF_056 | Completed |  | No Need | Done | ApplicationFinancialFacility_608 | Done
Sprint 2 | 305703 | AT_AFF_074 | Completed |  | Done | Done | ApplicationFinancialFacility_608 | Done | Need to do some
Sprint 2 | 305607 | AT_AFF_075 | Completed |  | No Need | Done | ApplicationFinancialFacility_608 | Done
Sprint 2 | 534131 | AT_AFF_076 | Not started | IMAL-6317 |  | Blocked |  |  | fixed
Sprint 2 | 534148 | AT_AFF_077 | Not started | IMAL-6316 |  | Blocked |  |  | fixed
Sprint 2 | 834966 | AT_AFF_098 | Not Completed | IMAL-6414 | Not Completed | Blocked | ApplicationFinancialFacility_608
Sprint 2 | 834967 | AT_AFF_099 | Not Completed | IMAL-6414 | Not Completed | Blocked | ApplicationFinancialFacility_608
Sprint 3 | 665923 | AT_RF_014 | Completed |  | Done | Done | RequestForFinancing_608 | Done
Sprint 3 | 666161 | AT_RF_024 | Completed |  | No Need | Done | RequestForFinancing_608 | Done
Sprint 3 | 678866 | AT_RF_032 | Not started | IIS KT Need |  | Descoped
Sprint 3 | 679200 | AT_RF_033 | Not started | IMAL-6458 |  | Blocked
Sprint 3 | 681303 | AT_RF_034 | Completed |  | Done | Done | RequestForFinancing_608 | Need to Execute
Sprint 3 | 680390 | AT_RF_035 | Completed |  | No Need | Done | RequestForFinancing_608 | Done
Sprint 4 | 640861 | AT_RF_040 | Completed |  | Done | Done | RequestForFinancing_608
Sprint 4 | 583893 | AT_RF_098 | Completed |  | Done | Done | WIFAK_Application_608
Sprint 4 | 583895 | AT_RF_099 | Completed |  | Done | Done | WIFAK_Application2
Sprint 4 | 582426 | AT_RF_100 | Completed |  | Done | Done | WIFAK_Application
Sprint 4 | 582480 | AT_RF_101 | Completed |  | Done | Done | WIFAK_Application2
Sprint 4 | 582565 | AT_RF_102 | Completed |  | Done | Done | WIFAK_Application
Sprint 5 | 739481 | AT_RF_157 | Completed |  | Done | Done | WIFAK_Application
Sprint 5 | 739576 | AT_RF_158 | Completed |  | Done | Done | Collateral_Management
Sprint 5 | 844419 | AT_RF_139 | Completed |  | Done | Done | WIFAK_Application
Sprint 5 | 844428 | AT_RF_140 | Completed |  | Done | Done | WIFAK_Application
Sprint 5 | 844429 | AT_RF_141 | Completed |  | No Need | Done | Request_For_Financing_608
Sprint 6 | 293979 | AT_FM_043 | Completed |  | Done |  | Request_For_Financing_608
Sprint 6 | 741265 | AT_FM_035 | Completed |  | Done | Done | FacilitiesManagement_608
Sprint 6 | 289236 | AT_FM_036 | Not started |  |  | Descoped
Sprint 6 | 288521 | AT_FM_037 | Not started |  |  | Descoped
Sprint 6 | 282194 | AT_FM_038 | Completed |  | Done | Done | WIFAK_Application2_608
Sprint 6 | 127881 | AT_FM_057 | Not started |  |  | Descoped
Sprint 6 | 127883 | AT_FM_058 | Completed |  | Done |  | WIFAK_Application_608
Sprint 6 | 140587 | AT_FM_059 | Completed | IMAL-7205 | Done | Blocked | WIFAK_Application_608
Sprint 7 | 402760 | AT_FM_078 | Not started | ITFC KT Need |  | Descoped
Sprint 7 | 1102235 | AT_FM_102 | Completed |  | Done |  | FacilitiesManagement_608
Sprint 7 | 1102236 | AT_FM_103 | Completed |  | Done |  | FacilitiesManagement_608
Sprint 7 | 1105452 | AT_FM_104 | Completed |  | Done |  | FacilitiesManagement_608
Sprint 7 | 1105461 | AT_FM_105 | Completed |  | Done |  | FacilitiesManagement_608
Sprint 7 | 1105462 | AT_FM_106 | Not started | FAC KT Need |  | Descoped
Sprint 7 | 949791 | AT_FP_001 | Completed |  | Done |  | FMSParameterFeature_608
Sprint 8 | 127834 | AT_DDR_020 | Completed |  | Done |  | DrawDownRequest_608
Sprint 8 | 127836 | AT_DDR_021 | Completed |  | Done |  | DrawDownRequest_608
Sprint 8 | 127921 | AT_DDR_022 | Completed |  | Done |  | DrawDownRequest_608
Sprint 8 | 127922 | AT_DDR_023
Sprint 8 | 135019 | AT_DDR_024
Sprint 8 | 135022 | AT_DDR_025

## AllFeaturesTestDataInstructions
TestDataCellLegend | Test Data Type | Remarks
| Values Updated Automatically | Values Automatically upadated From Automation Script
| Select Value - DropDown Values | Drop Values Values Configured in sheet based on parameters
| Editable field | Need to Change data for Every Execution
| Fixed Value | No need to change data Every run

## CSMParam_Login
UserType | UserName | Password | CompanyCode | BranchCode
FMS_User1 | MODEL.B | 123 | 1 | 1
FMS_User2 | SANKAR | 321 | 1 | 1

## CSM_Login
UserType | UserName | Password | CompanyCode | BranchCode
CSM_User1 | MODEL.B | 123 | 1 | 1
CSM_User2 | SANKAR | 321 | 1 | 1

## FMS_Login
UserType | UserName | Password | CompanyCode | BranchCode
FMS_User1 | VAK | 321 | 1 | 1
FMS_User2 | SANKAR | 321 | 1 | 1

## FMSParam_login
UserType | UserName | Password | CompanyCode | BranchCode
FMS_ParamUser1 | MODEL.B | 123 | 1 | 1
FMS_ParamUser2 | SANKAR | 321 | 1 | 1

## IISParam_Login
UserType | UserName | Password | CompanyCode | BranchCode
IIS_ParamUser1 | SANKAR | 321 | 1 | 1
IIS_ParamUser2 | MODEL.B | 123 | 1 | 1

## SadsLogin
UserType | UserName | Password
SADS_User1 | SYSADM | 123
SADS_User2 | SYSADM1 | 123

## TestExecution
Sequence | TestCaseID | Data Set ID | ExecuteYes/No | Dependent Test Case Id_One | Dependent Test Case Id_Two | Dependent Test Case Id_Three | Dependent Test Case Id_Four | Dependent Test Case Id_Five | Dependent Data Set Id_Five
1 | Fms_01 | Fms_01_D1 | No
2 | 862019 | DS01_862019 | Yes
3 | 843959 | DS01_843959 | Yes
4 | 296063 | DS01_296063 | Yes
5 | 305703 | DS01_305703 | Yes
6 | 834966 | DS01_834966 | Yes
7 | 681303 | DS01_681303 | Yes
8 | EndExecution | EndExecution | Yes

## IIS_Param_TestData
TestCaseID | DataSet ID | Class | No of payment input | No of Payment Select | Application For | CIF No | Facility Type | Country of Financing | Facility Rating | Total value | Expire Date | Product Class
AT_RF_014 | DS_AT_RF_014 | 1 | 60 | Nearest 1 | New Facility | 727 | 369 | 320 | 2 | 10000 | 31/5/2023 | 1

## FMS_WIFAK_ApplicationTestData
Feature Name | TestCaseID | DataSet ID | Search Code | Collateral | Collaterals defined | Application For | Facility Ref | CIF No | Facility Type | Country of Financing | Facility Rating | Total value | Expire Date | Finance Amount | Down Payment % | Down Payment to Vendor % | Limit Details Item | Product Class | Margin Rate | CV Value | No of Payments | Charges Details Code | Document Code | File Location | Line No | Solicitor Name | Estimator Name | Send Alert User | Reference Code | Decision | Forward To | Decision3 | Recommendation | More Comments
| AT_AFF_098 | DS_AT_AFF_098 | 369 |  |  | New Facility |  | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 |  |  |  |  | 1 | [7 empty] | 1 | 1 |  |  | Approve
RequestForFinancing_608 | AT_RF_034 | DS_AT_RF_034 | 369 |  |  | New Facility |  | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 |  |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 | 1 |  |  | Approve
RequestForFinancing_608 | AT_RF_040 | DS_AT_RF_040 |  |  |  | New Facility |  | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 |  | 2 | 2 |  | 1
| AT_RF_098 | DS_AT_RF_098 | 3679 | [29 empty] | Approve | Test Comments
| AT_RF_099 | DS_AT_RF_099 | 369 | Application Level | Sublimit | New Facility |  | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 |  |  |  |  | 1 | [7 empty] | 1 | 1 |  |  | Approve
| AT_RF_100 | DS_AT_RF_100 |  |  |  | Decrease | 1349 |  |  |  | 2 | 500 | 01/05/2024 | [12 empty] | 1 | 1 |  |  | Approve
| AT_RF_101 | DS_AT_RF_101 | 369 |  |  | New Facility |  | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 |  |  |  |  | 1 |  |  |  |  | 3455 |  | 2 | 1 | 1 |  |  | Approve
| AT_RF_102 | DS_AT_RF_102 |  |  |  | New Facility |  | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 |  |  |  | Import L/C |  | 2 | [6 empty] | 1 | 1 |  |  | Approve
| AT_RF_139 | DS_AT_RF_139 |  |  |  | New Facility |  | 727 | 369 | 320 | 2 | 1000 | 01/05/2024 |  |  |  |  | 1 | [7 empty] | 1 | 1 |  |  | Approve
| AT_RF_140 | DS_AT_RF_140 |  |  |  | New Facility |  | 727 | 369 | 320 | 2 | 1000 | 01/05/2024 |  |  |  |  | 1 | [5 empty] | C:\\Users\\inindc00608\\Desktop\\FMSTest.txt |  | 1 | 1 |  |  | Approve
| AT_FM_038 | DS_AT_FM_038 | 369 |  |  | New Facility |  | 727 | 369 | 320 | 2 | 1000 | 01/05/2024 |  |  |  |  | 1 | [7 empty] | 1 | 1 |  |  | Forward | Approve Level 3 | Approve
| AT_FM_058 | DS_AT_FM_058 |  |  |  | New Facility |  | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 |  |  |  |  | 1 |  |  | 10 |  |  |  |  | 1 | 1 |  |  | Forward | Approve Level 3 | Approve
| AT_FM_059 | DS_AT_FM_059 |  |  |  | New Facility |  | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 |  |  |  |  | 1 | [7 empty] | 1 | 1 | VAK

## RequestForFinancingTestData
TestCaseID | DataSet ID | Search Code | Application For | CIF No | Facility Type | Country of Financing | Facility Rating | Total value | Expire Date | Down Payment % | Down Payment to Vendor % | Charges Details Code | Facility Ref | Description | Value Date | FC Amount | Facility Type | Committee Member | Reason For Submission | Customer CIF | Total Limit | Product Class | Margin Value | No of Payments | Request Code | Approve1 Decision | Decision Forward To | Approval Committee | Recommendation | Solicitor Name | Estimator Name | Decision
AT_RF_034 | DS_AT_RF_034 | 369 | New Facility | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 |  |  | 1 |  |  |  | 500 | [5 empty] | 1 | [7 empty] | 1 | 1 | Approve
AT_RF_040 | DS_AT_RF_040 |  | New Facility | 727 | 369 | 320 | 2 | 20000 | 01/05/2024 | 2 | 2 | [10 empty] | 1
AT_RF_157 | DS_AT_RF_157 | [11 empty] | 1471 | Test | 05/01/2024 | 500
AT_FM_043 | DS_AT_FM_043 | [15 empty] | 19 | At Least One Member | New Request | 727 | 100 | 1 | 1 |  | 4123 | Forward | Approval Committee | Investment Committee | Approved
AT_FM_058 | DS_AT_FM_058 | [15 empty] | 19 |  | New Request | 727 | 1000 | 1 |  | 10 |  | Approve

## FMS_Collateral_Management
TestCaseID | DataSet ID | Collateral Type | Valid From Date | Valid To Date | Brief Description | Long Description | Collateral Currency | Amount | Asset Type
AT_RF_158_Core | DS01_AT_RF_158 | 564 | 05/01/2022 | 05/01/2024 | Test | Test | 840 | 1000
AT_RF_158_Param | DS02_AT_RF_158 | 1270 |  |  | Test | Test |  |  | Cash

## Draw_Down_Request
TestCaseID | DataSet ID | Facility Ref | Description | Value Date | FC Amount
AT_RF_157 | DS01_AT_RF_157 | 1586 | Test | 05/01/2024 | 500

## FacilitiesManagementTestData
TestCaseID | DataSet ID | Application For | CIF No | Facility Type | Country of Financing | Facility Rating | Total value | Expire Date | Product Class | No of Payments | Solicitor Name | Estimator Name | Reference Code | Decision | Forward To | Decision3 | Solicitor Date Sent | Solicitor Date Received | Estimator Date Sent | Estimator Date Received | Custodian Date Sent | New Facility Rating | Suspend Reason
AT_FM_035 | DS_AT_FM_035 |  | 671
AT_FM_058 | DS_AT_FM_058 | New Facility | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 | 1 | 10 | 1 | 1 |  | Forward | Approve Level 3 | Approve
AT_FM_102 | DS_AT_FM_102 | New Facility | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 | 1 |  | 1 | 1 |  |  |  | Approve
AT_FM_103 | DS_AT_FM_103 | New Facility | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 | 1 | 10 | 1 | 1 |  | Forward | Approve Level 3 | Approve
AT_FM_104 | DS_AT_FM_104 | New Facility | 727 | 369 | 320 | 2 | 1000 | 01/05/2024 | 1 | 10 | 1 | 1 |  | Forward | Approve Level 3 | Approve
AT_FM_105 | DS_AT_FM_105 | New Facility | 727 | 369 | 320 | 2 | 1000 | 01/05/2024 | 1 | 10 | 1 | 1 | 4434 | Forward | Approve Level 3 | Approve | 28/06/2023 | 28/06/2023 | 28/06/2023 | 28/06/2023 | 28/06/2023 | 3 | 26

## ApplicationFinancialFacility
TestCaseID | DataSet ID | Country Code | Search Code | Application For | CIF No | Facility Type | Country of Financing | Facility Rating | Total value | Expire Date | Product Class | Solicitor Name | Estimator Name | Reference Code | BM Recommends | Decision3
AT_AFF_036 | DS_AT_AFF_036 |  |  | New Facility | 727 | 369 | 320 | 2 | 1000 | 01/05/2024 | 600
AT_AFF_040 | DS_AT_AFF_040 | [12 empty] | 3451
AT_AFF_048 | DS_AT_AFF_048 |  |  | New Facility | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 | 1 | 1 | 1 |  |  | Approve
AT_AFF_052 | DS_AT_AFF_052 | [13 empty] | FMS Test
AT_AFF_074 | DS_AT_AFF_074 | 320
AT_AFF_098 | DS_AT_AFF_098 |  | 369 | New Facility | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 | 1 | 1 | 1 |  |  | Approve

## FMSParameterTestData
TestCaseID | DataSet ID | Application For | CIF No | Facility Type | Country of Financing | Facility Rating | Total value | Expire Date | Product Class | Floating Rate | FR Periodicity | FR Periodicity Type | Solicitor Name | Estimator Name | Reference Code | Decision | Forward To | Decision3
AT_FP_001 | DS_AT_FP_001 | New Facility | 727 | 369 | 320 | 2 | 10000 | 01/05/2024 | 2 | 98 | 2 | Month(s) | 1 | 1 |  | Forward | Approve Level 3 | Approve

## DrawDownRequestTestData
TestCaseID | DataSet ID | Search Code | Application For | Reason For Submission | Customer CIF | CIF No | Facility Type | Total Limit | Country of Financing | Facility Rating | Total value | Expire Date | Down Payment Percent | Down Payment Amount | Product Class | Floating Rate | FR Periodicity | FR Periodicity Type | Solicitor Name | Estimator Name | Reference Code | Request Code | Decision | Forward To | Decision3 | Facility Ref | Description | Value Date | FC Amount | DD Code | From Code | To Code
AT_DDR_020 | DS_AT_DDR_020 | 369 | New Facility |  |  | 727 | 369 |  | 320 | 2 | 10000 | 01/05/2024 | 20 |  | 1 |  |  |  | 1 | 1 |  |  | Forward |  | Approve
AT_DDR_021 | DS_AT_DDR_021 | 369 | New Facility | New Request | 727 | 727 | 19 | 25000 | 320 | 2 | 10000 | 01/05/2024 | 20 |  | 1 | [7 empty] | Approve
AT_DDR_022 | DS_AT_DDR_022 | 369 | New Facility |  |  | 727 | 369 |  | 320 | 2 | 15000 | 01/05/2024 | 20 |  | 2 | 98 | 2 | Month(s) | 1 | 1 |  |  |  |  | Approve | 1587 | Test Sankar | 05/01/2024 | 1000
AT_DDR_023 | DS_AT_DDR_023 | 369 | New Facility |  |  | 727 | 369 |  | 320 | 2 | 20000 | 01/05/2024 |  |  | 2 | 98 | 2 | Month(s) | 1 | 1 |  |  |  |  | Approve |  | Test Sankar | 05/01/2024 | 500
AT_DDR_024 | DS_AT_DDR_024 | 369 | New Facility |  |  | 727 | 369 |  | 320 | 2 | 25000 | 01/05/2024 |  |  | 1 |  |  |  | 1 | 1 |  |  |  |  | Approve |  | Test Sankar | 05/01/2024 | 500 |  | 1000 | 1030