## AllFeaturesTestExecutionInfo
Sprint Details | Test Case ID | Test ID | Scirpting | Defect ID | Test Data | Status of Execution | Feature File Nam
Sprint-1 | 862778 | AT_AFF_038 | partially completed/blocked | yet to get defect id from johns | partially completed/blocked | partially completed/blocked | Application for Financial Facility
Sprint-1 | 771445 | AT_AFF_042 | completed/blocked |  | completed/blocked | completed/blocked | Application for Financial Facility
Sprint-1 | 280446 | AT_AFF_046 | Forward to sprint 2 |  | Forward to sprint 2 | Forward to sprint 2 | Application for Financial Facility
Sprint-1 | 299876 | AT_AFF_050 | KT not given for IIS application | KT not given for IIS application | KT not given for IIS application | KT not given for IIS application | Application for Financial Facility
Sprint-1 | 299492 | AT_AFF_054 | KT not given for IIS application | KT not given for IIS application | KT not given for IIS application | KT not given for IIS application | Application for Financial Facility
Sprint-1 | 347028 | AT_AFF_058 | Johns have doubt on this | Johns have doubt on this | Johns have doubt on this | Johns have doubt on this | Application for Financial Facility
Sprint-2 | 280446 |  | completed | completed | completed | completed | Application for Financial Facility
Sprint-2 | 585803 |  | completed | completed | completed | completed | Application for Financial Facility
Sprint-2 | 570631 |  | blocked | blocked | blocked | blocked | Application for Financial Facility
Sprint-2 | 127917 | AT_AFF_065 | completed | completed | completed | completed | Application for Financial Facility
Sprint-2 | 127925 | AT_AFF_066 | partially completed/blocked | partially completed/blocked | partially completed/blocked | partially completed/blocked | Application for Financial Facility
Sprint-2 | 127926 | AT_AFF_067 | completed | completed | completed | completed | Application for Financial Facility
sprint-3 | 127925 | AT_AFF_066 | partially completed/blocked | partially completed/blocked | partially completed/blocked | partially completed/blocked | Application for Financial Facility
sprint-3 | 678142 | AT_RF_029 | completed | completed | completed | completed | Request For Financing
sprint-3 | 678143 | AT_RF_030 | descoped/duplicate | descoped/duplicate | descoped/duplicate | descoped/duplicate | Request For Financing
sprint-3 | 678324 | AT_RF_031 | completed | completed | completed | completed | Request For Financing
sprint-3 | 653133 | AT_RF_036 | Hold by johns,due to Maintenance is not working | Hold by johns,due to Maintenance is not working | Hold by johns,due to Maintenance is not working | Hold by johns,due to Maintenance is not working | Request For Financing
sprint-3 | 654404 | AT_RF_039 | blocked | blocked | blocked | blocked | Request For Financing
sprint-3 | 640897 | AT_RF_042 | completed | completed | completed | completed | Request For Financing
sprint-3 | 640956 | AT_RF_043 | completed | completed | completed | completed | Request For Financing
sprint-4 | 434947 | AT_RF_076 | completed | completed | completed | completed | Request For Financing
sprint-4 | 654367 | AT_RF_038 | blocked | blocked | blocked | blocked | Request For Financing
sprint-4 | 640874 | AT_RF_041 | completed | completed | completed | completed | Request For Financing
sprint-4 | 468154 | AT_RF_077 | Descoped | Descoped | Descoped | ITFC related | Request For Financing
sprint-4 | 468161 | AT_RF_078 | Descoped | Descoped | Descoped | ITFC related | Request For Financing
sprint-4 | 468167 | AT_RF_079 | Descoped | Descoped | Descoped | ITFC related | Request For Financing
sprint-4 | 584047 | AT_RF_110 | Descoped | Descoped | Descoped | ITFC related | Request For Financing
sprint-4 | 584557 | AT_RF_111 | completed | completed | completed | completed | Request For Financing
sprint-4 | 585161 | AT_RF_112 | blocked | blocked | blocked | blocked | Request For Financing
sprint-4 | 584744 | AT_RF_114 | completed | completed | completed | completed | Request For Financing
sprint-5 | 771445 | AT_AFF_042 | need to write script for param |  | need to write script for param | need to write script for param | Application for Financial Facilities
sprint-5 | 299876 | AT_AFF_050 | Descoped |  | Descoped | Descoped | Application for Financial Facilities
sprint-5 | 299492 | AT_AFF_054 | Descoped |  | Descoped | Descoped | Application for Financial Facilities
sprint-5 | 749202 | AT_RF_151 | completed |  | need to do | need to do | Request For Financing
sprint-5 | 759182 | AT_RF_152 | completed |  | need to do | need to do | Request For Financing
sprint-5 | 127919 | AT_RF_168 | completed |  | need to do | need to do | Request For Financing
sprint-5 | 127920 | AT_RF_169 | completed |  | need to do | need to do | Request For Financing
sprint_6 | 808942 | AT_FM_029 | completed |  | need to do | need to do | Facilities Management
sprint_6 | 809575 | AT_FM_030 | completed |  | need to do | need to do | Facilities Management
sprint_6 | 841963 | AT_FM_031 | completed |  | need to do | need to do | Facilities Management
sprint_6 | 850741 | AT_FM_032 | blocked | IMAL_6538 | defect | defect | Facilities Management
sprint_6 | 868316 | AT_FM_033 | blocked | db related issue, request from johns to hold | others | others | Facilities Management
sprint_6 | 127874 | AT_FM_055 | blocked | FMS Part completed, IIS Clarification required | others | others | Facilities Management
sprint_6 | 127878 | AT_FM_056 | blocked | FMS Part completed, IIS Clarification required | others | others | Facilities Management
sprint_7 | 396824 | AT_FM_079 | Blocked | Defect/ IMAL-7379 | Blocked | Blocked | Facilities Management
sprint_7 | 586558 | AT_FM_090 | completed/Blocked | Defect/IMAL-7332 | need to do | Blocked | Facilities Management
sprint_7 | 586526 | AT_FM_091 | completd |  | need to do | need to do | Facilities Management
sprint_7 | 586527 | AT_FM_092 | completed/Blocked | Defect/IMAL-7332 | need to do | Blocked | Facilities Management
sprint_7 | 586528 | AT_FM_093 | Descoped/Duplicate TC | Descoped/Duplicate TC |  |  | Facilities Management
sprint_7 | 827643 | AT_FM_094 | Blocked | Defect/IMAL-7440 | Blocked | Blocked | Facilities Management
sprint_7 | 827644 | AT_FM_095 | Blocked | Defect/IMAL-7440 | Blocked | Blocked | Facilities Management
sprint_7 | 140587 | AT_FM_059 | completed | completed | completed | completed | Facilities Management
sprint_8 | 140601 | AT_DDR_026 | completed | completed | completed | completed | Draw Down Request
sprint_8 | 326293 | AT_DDR_027 | ITFC training required | ITFC training required | ITFC training required | ITFC training required | Draw Down Request
sprint_8 | 316166 | AT_DDR_028 | completed |  |  |  | Draw Down Request
sprint_8 | 326280 | AT_DDR_029 | ITFC training required | ITFC training required | ITFC training required | ITFC training required | Draw Down Request
sprint_8 | 402676 | AT_DDR_030 | Fms Part need to do IIS part pending due to clarifications needed | Fms Part need to do IIS part pending due to clarifications needed | Fms Part need to do IIS part pending due to clarifications needed | Fms Part need to do IIS part pending due to clarifications needed | Draw Down Request
sprint_8 | 879358 | AT_CM_009 | completed | completed | completed | completed | Collateral Management
sprint_9 | 127860 | AT_CM_046 | completed |  | completed | completed | Collateral Management
sprint_9 | 1057761 | AT_CM_047 | Defect | Webservice on Hold | Defect | Defect | Collateral Management
sprint_9 | 1057762 | AT_CM_048 | Defect | Webservice on Hold | Defect | Defect | Collateral Management
sprint_9 | 1057763 | AT_CM_049 | Defect | Webservice on Hold | Defect | Defect | Collateral Management
sprint_9 | 1090798 | AT_CM_050 | Defect | IMAL-7555 | Defect | Defect | Collateral Management
sprint_9 | 1090800 | AT_CM_051 | Defect | IMAL-7555 | Defect | Defect | Collateral Management
sprint_9 | 1090801 | AT_CM_052 | Defect | IMAL-7555 | Defect | Defect | Collateral Management
sprint_9 | 1090803 | AT_CM_053 | Defect | IMAL-7555 | Defect | Defect | Collateral Management
sprint_9 | 1166910 | AT_CM_054 | descoped | IIS related, clarifications needed | descoped | descoped | Collateral Management
sprint_9 | 616977 | AT_CA_021 | completed | completed | completed | completed | Committee Approval
sprint_9 | 1265137 | AT_CA_022 | completed | completed | completed | completed | Committee Approval
sprint_9 | 1265138 | AT_CA_023 | completed | completed | completed | completed | Committee Approval
sprint_9 | 280606 | AT_CM_030 | completed | completed | completed | completed | Collateral Management
sprint 10 | 956327 | AT_RP_001 | completed | completed | completed | completed | Repayment Plan
sprint 10 | 651656 | AT_RP_002 | completed | completed | completed | completed | Repayment Plan
sprint 10 | 594207 | AT_RP_003 | completed | completed | completed | completed | Repayment Plan
sprint 10 | 816212 | AT_RP_004 | completed | completed | completed | completed | Repayment Plan
sprint 10 | 834702 | AT_RP_005 | completed | completed | completed | completed | Repayment Plan
sprint 10 | 857301 | AT_RP_006 | completed | completed | completed | completed | Repayment Plan
sprint 11 | 140567 | AT_CG_017 | Defect | IMAL-8369 |  |  | Customer Grading
sprint 11 | 140632 | AT_CG_018 | Defect | IMAL-8369 |  |  | Customer Grading
sprint 11 | 140707 | AT_CG_019 | descoped | Duplicate |  |  | Customer Grading
sprint 11 | 288807 | AT_CG_020 | completed | completed | completed | completed | completed
sprint 11 | 953616 | AT_AE_001 | Defect | IMAL-7555 |  |  | Accounting Entries
sprint 11 | 953616 | AT_AE_001_01 | completed | completed | completed | completed | completed
sprint 11 | 834132 | AT_AE_002 | completed | completed | completed | completed | completed
sprint 11 | 834132 | AT_AE_002_01 | completed | completed | completed | completed | completed
Sprint 12 | 128351 | AT_AD_004 | completed | completed | completed | completed | Accrual Deal
Sprint 12 | 128352 | AT_AD_005 | completed | completed | completed | completed | Accrual Deal
Sprint 12 | 128354 | AT_AD_007 | completed | completed | completed | completed | Accrual Deal
Sprint 12 | 128355 | AT_AD_008 | Carryforwarded to sprint 13 | Carryforwarded to sprint 13 | Carryforwarded to sprint 13 | Carryforwarded to sprint 13 | Accrual Deal
Sprint 12 | 827643 | AT_FM_094 | completed | completed | completed | completed | Facilities Management
Sprint 12 | 827644 | AT_FM_095 | completed | completed | completed | completed | Facilities Management
sprint 13 | 128355 | AT_AD_008 |  |  |  |  | Accrual Deal
sprint 13 | 128353 | AT_AD_006 |  |  |  |  | Accrual Deal
sprint 13 | 128356 | AT_AD_009 |  |  |  |  | Accrual Deal
sprint 13 | 131160 | AT_AP_013 |  |  |  |  | Accrual Process
sprint 13 | 131585 | AT_AP_014 |  |  |  |  | Accrual Process

## AllFeaturesTestDataInstructions
TestDataCellLegend | Test Data Type | Remarks
| Values Updated Automatically | Values Automatically upadated From Automation Script
| Select Value - DropDown Values | Drop Values Values Configured in sheet based on parameters
| Editable field | Need to Change data for Every Execution
| Fixed Value | No need to change data Every run

## FMS_Login
UserType | UserName | Password | CompanyCode | BranchCode
FMS_User1 | MODEL.B | 123 | 1 | 1
FMS_User2 | CHRISAG | 321 | 1 | 1
FMS_User3 | AJITH | 321 | 1 | 1
FMS_User4 | SANKAR | 321 | 1 | 1
FMS_User5 | JAY | 321 | 1 | 1
FMS_User6 | SNEHA | 321 | 1 | 1
FMS_User7 | KOUSALYA | 321 | 1 | 1
FMS_User8 | ARUL | 321 | 1 | 1
FMS_User9 | PRIYANKA | 321 | 1 | 1
FMS_User10 | RAJAT | 321 | 1 | 1
FMS_User11 | VIJAYK | 321 | 1 | 1
FMS_User12 | GOWTHAM | 321 | 1 | 1

## FMSParam_login
UserType | UserName | Password | CompanyCode | BranchCode
FMS_ParamUser1 | MODEL.B | 123 | 1 | 1
FMS_ParamUser2 | CHRISAG | 321 | 1 | 1
FMS_ParamUser3 | AJITH | 321 | 1 | 1
FMS_ParamUser4 | SANKAR | 321 | 1 | 1
FMS_ParamUser5 | JAY | 321 | 1 | 1
FMS_ParamUser6 | SNEHA | 321 | 1 | 1
FMS_ParamUser7 | KOUSALYA | 321 | 1 | 1
FMS_ParamUser8 | ARUL | 321 | 1 | 1
FMS_ParamUser9 | PRIYANKA | 321 | 1 | 1
FMS_ParamUser10 | RAJAT | 321 | 1 | 1
FMS_ParamUser11 | VIJAYK | 321 | 1 | 1
FMS_ParamUser12 | GOWTHAM | 321 | 1 | 1

## SadsLogin
UserType | UserName | Password
SADS_User1 | SYSADM | 123
SADS_User2 | SYSADM1 | 123

## TestExecution
Sequence | TestCaseID | Data Set ID | ExecuteYes/No | Dependent Test Case Id_One | Dependent Test Case Id_Two | Dependent Test Case Id_Three | Dependent Test Case Id_Four | Dependent Test Case Id_Five | Dependent Data Set Id_Five
1 | Fms_01 | Fms_01_D1 | No
2 | EndExecution | EndExecution | Yes

## FMS_AppforFinancialfacility
Test Case ID | Data Set ID | CIF NO | Facility Type | Country of Financing | Facility Rating | Total value | Expiry Date | Solicitor Name | Estimators Name | No Of Payment | PCValue | Floating Rate | FRPeriodicity | AFFYieldetails | AFFMarginRate | SolicitorName | EstimatorName | FMYieldetails | FMMarginRate | DrawDownType | ValueDate | ProductClass | DiscriptionEng | DiscriptionArab
127878 | AT_FM_056 | 727 | 369 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1
1265137 | AT_CA_022 | 727 | 369 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1
1265138 | AT_CA_023 | 727 | 369 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1
616977 | AT_CA_021 | 727 | 369 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1
585803 | AT_AFF_091 | 727 | 369 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1
956327 | AT_RP_001 | 727 | 369 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1
594207 | AT_RP_003 | 727 | 369 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1 | 70
834702 | AT_RP_005 | 727 | 369 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1
816212 | AT_RP_004 | 727 | 369 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1 | 70
434947 | AT_RF_076 | 727 | 369 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1 |  | 5588 |  | 2 | 11 | 2 | 1 | 1 | 15 | 5
678142 | AT_RF_029 | 727 | 697 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1 | 70
808942 | AT_FM_029 | 727 | 697 | 320 | 2 | 10000 | 10/10/2024 | 1 | 1 |  | 1 | [8 empty] | 1 | 16/01/2021 | 1 | Data | Data

## FMS_CollateralManagement
Test Case ID | Data Set ID | Collateral Type | Valid From Date | Valid To Date | Brief Description | Long Description | Collateral Currency | Amount
280606 | AT_CM_030 | 564 | 16/01/2021 | 24/09/2023 | Testdata | Testdata | 840 | 1000

## RequestForFinancing
TestCaseID | DataSet ID | Search Code | Application For | CIF No | Facility Type | Country of Financing | Facility Rating | Total value | Expire Date | Committee Member | Reason For Submission | Customer CIF | Total Limit | Product Class | Margin Value | No of Payments | Solicitor Name | Estimator Name | Send Alert User | Reference Code | Decision | Forward To | Approval Committee | Recommendation | Decision3 | Solicitor Date Sent | Solicitor Date Received | Estimator Date Sent | Estimator Date Received | Custodian Date Sent | New Facility Rating | Suspend Reason | Drawdowntype | DiscriptionEnglish | Discriptionarab | Datesubmitted | Valuedate
127920 | AT_RF_169 |  |  |  | 19 |  |  |  |  | At Least One Member | New Request | 727 | 100 | 1 | 1 | [5 empty] | Forward | Approval Committee | Investment Committee | Approved | [8 empty] | 1 | Request | Request | 15/01/2021 | 15/01/2021